## Open Issues
Issue ID | Title | Type | Priority | Raised By | Date | Due | Assignee | Status
ISS-001 | Control plan not updated per FMEA Rev 1.2 | Quality | HIGH | C. Fischer | 2024-05-14 | 2024-06-01 | S. Klaas | OVERDUE
ISS-002 | DEV-002 SOC accuracy roadmap required | Technical | HIGH | P. Reiter | 2024-07-18 | 2024-08-01 | T. Weber | IN PROGRESS
ISS-003 | EMC pre-compliance test not scheduled | Testing | MEDIUM | M. Hartmann | 2024-07-18 | 2024-10-15 | M. Hartmann | PLANNED
ISS-004 | ADC self-calibration implementation (AI-001) | Technical | MEDIUM | M. Hartmann | 2024-04-05 | 2024-09-15 | T. Weber | DELAYED
ISS-005 | TITAN ABW-004 safety escalation | Safety | CRITICAL | G. Huber | 2024-08-20 | 2024-09-15 | Apex Eng. | OPEN
ISS-006 | ISO 21434 full audit completion | Compliance | HIGH | T. Weber | 2024-06-20 | 2024-12-01 | T. Weber | IN PROGRESS
ISS-007 | CAN-FD gateway compatibility test pending | Interface | MEDIUM | K. Meier | 2024-07-18 | 2024-09-15 | K. Meier | PLANNED
ISS-008 | IP67 housing design for SOP | Design | LOW | S. Klaas | 2024-07-15 | 2025-03-01 | S. Klaas | PLANNED
ISS-009 | Dual-source ADC qualification | Supply | MEDIUM | P. Reiter | 2024-08-01 | 2025-01-15 | P. Reiter | OPEN
ISS-010 | Vertex re-audit closure confirmation | Quality | HIGH | R. Schmidt | 2024-05-14 | 2024-08-15 | R. Schmidt | CLOSED - passed