## Project Milestones
Milestone ID | Description | Planned Date | Actual Date | Status | Owner | Remarks
M1 | Project Kickoff | 2024-01-10 | 2024-01-10 | COMPLETE | P. Reiter | On schedule
M2 | SRS Baseline (Rev 1.0) | 2024-01-20 | 2024-01-15 | COMPLETE | T. Weber | 5 days early
M3 | IRS Baseline | 2024-02-15 | 2024-02-28 | COMPLETE | S. Klaas | 13 days late - LIN spec added
M4 | FMEA Initial Baseline | 2024-02-28 | 2024-02-10 | COMPLETE | M. Hartmann | Early release
M5 | HW Design Review (Rev A) | 2024-03-15 | 2024-03-20 | COMPLETE | S. Klaas | Minor delay
M6 | Supplier Quality Audit | 2024-05-01 | 2024-05-14 | COMPLETE | C. Fischer | Conditionally approved
M7 | HW Prototype (Rev B) | 2024-04-30 | 2024-05-10 | COMPLETE | S. Klaas | PCB re-spin needed
M8 | SRS Rev 2.0 Release | 2024-06-15 | 2024-06-20 | COMPLETE | T. Weber | Cybersec added
M9 | HW Pre-Production (Rev C) | 2024-07-01 | 2024-07-15 | COMPLETE | S. Klaas | IP67 pending
M10 | Pre-production Test Report | 2024-08-31 | 2024-09-10 | COMPLETE | M. Hartmann | All PASS
M11 | Vehicle Integration Start | 2024-09-02 | 2024-09-02 | IN PROGRESS | K. Meier | IP54 waiver active
M12 | EMC Pre-compliance | 2024-10-15 |  | PLANNED | M. Hartmann | Lab slot reserved
M13 | ISO 21434 Cybersec Audit | 2024-12-01 |  | PLANNED | T. Weber | External auditor TBD
M14 | Production Approval (PPAP) | 2025-03-01 |  | PLANNED | R. Schmidt | Pending all closures
M15 | Start of Production (SOP) | 2025-06-01 |  | PLANNED | P. Reiter | Target date

## Gate Status
Gate | Criteria | Status | Blocking Issues
G1 - Concept | SRS baseline, FMEA started | PASSED | None
G2 - Design | FMEA complete, HW design reviewed | PASSED | None
G3 - Pre-prod | PP test pass, audit conditional | PASSED | IP67 waiver, SOC deviation open
G4 - Integration | Vehicle test complete, EMC pass | IN PROGRESS | EMC pending, ISO 21434 pending
G5 - SOP | PPAP approved, all deviations closed | NOT STARTED | Multiple open items