## Risk Register
Risk ID | Description | Category | Probability | Impact | Score | Mitigation | Owner | Status
R-001 | SOC algorithm accuracy below spec | Technical | High | Medium | 12 | SW fix in v2.2 targeted Q4 | T. Weber | OPEN - DEV-002
R-002 | ISO 21434 audit failure / late completion | Compliance | Medium | High | 12 | External consultant engaged | T. Weber | OPEN - monitoring
R-003 | NTC redundancy cost increase | Cost | Low | Medium | 4 | Redesign absorbed in HW Rev C | S. Klaas | CLOSED
R-004 | EMC failure requiring PCB re-spin | Technical | Medium | High | 12 | Early pre-compliance test | M. Hartmann | OPEN - test pending
R-005 | Supplier audit major findings not closed | Quality | Low | High | 8 | Re-audit scheduled Aug 2024 | R. Schmidt | CLOSED - re-audit pass
R-006 | CAN-FD integration issue with gateway ECU | Interface | Medium | Medium | 9 | Joint integration test Sept | K. Meier | OPEN - in progress
R-007 | IP67 housing not ready for SOP | Design | Low | Medium | 4 | IP67 housing Rev D planned | S. Klaas | OPEN - DEV-001 waiver
R-008 | TITAN chassis deviation ABW-004 unresolved | Safety | Medium | High | 12 | FEM analysis by Apex | G. Huber | OPEN - safety-critical
R-009 | Key supplier single-source for ADC chip | Supply | Low | High | 8 | Dual-source qualification | P. Reiter | OPEN - action Q1 2025
R-010 | Documentation delays PPAP submission | Process | Low | Low | 2 | Doc tracker established | R. Schmidt | CLOSED